## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 10.11.2021 11:43
Group Number |  | 14
Participant 1 |  | Brandenburg Jonas
Participant 2 |  | Dohnalek Raphael
Participant 3 |  | Duskanich Markus
Participant 4 |  | Duskanich Michael
Participant 5 |  | Meindl Tobias
Mentor |  | Eckkrammer Florian
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Developer wants to have a architecture structure plan | 2:23 | 2:23 | 0 | 1
2 | Developer wants to get used to backend stack | 3:00 | 0:00 | -0.125 |  |  | will be postponed until actual start
3 | Developer wants to decide on a Database | 2:47 | 2:47 | 0 | 1
4 | Developer wants to get informed about angular | 6:08 | 6:08 | 0 | 1
5 | Developer wants to get used to their documentation tool | 0:59 | 0:59 | 0 | 1
6 | Stakeholder wants a visual prototype for early feedback / decision making | 21:37 | 21:37 | 0 |  |  | meant to strech over two sprints
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -0.125 | 4 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol